## Solar Summary
NJCEP Direct Grid Supply Solar Installed Projects As Of 10/31/14
Description | Project Qty | Total Capacity (KW dc) | Percent of Capacity
EDC Projects | 76 | 78465.059 | 29.49%
Subsection q | 6 | 32495.03 | 12.21%
Subsection r | 0 | 0 | 0%
Subsection s | 3 | 12687.7 | 4.77%
Subsection t | 1 | 19880.56 | 7.47%
Other | 33 | 122525.716 | 46.05%
Installed Totals | 119 | 266054.065 | 99.99%
NJCEP Direct Grid Supply Solar Project Pipeline As Of 10/31/14
Description | Project Qty | Total Capacity (KW dc) | Percent of Capacity
EDC Projects | 0 | 0 | 0%
Subsection q | 29 | 198747 | 69.82%
Subsection r | 0 | 0 | 0%
Subsection s | 0 | 0 | 0%
Subsection t | 5 | 42795 | 15.03%
Other | 4 | 43101.7 | 15.14%
Pipeline Totals | 38 | 284643.7 | 99.99%
Grid Supply Solar Installed Projects Plus Pipeline Projects As Of 10/31/14
| Project Qty | Total Capacity (KW dc)
Grid Supply Totals | 157 | 550697.765
Note 1: The projects summarized in the above Pipeline table are based upon solar projects that have been accepted by the NJCEP but have not yet reached the "Installed Project" status. Based upon historical data, some percent of these projects will not be completed due to various reasons. This report is a snapshot of the program activity as of the report date. Other projects that may be under various stages of review are not reported here if the SRP Acceptance letter has not been issued yet.

## Subsection q
NJCEP Subsection q Project Summary By Energy Year As Of 10/31/14
| Subsection q Installed Projects |  | Subsection q Project Pipeline |  | Subsection q Installed Projects Plus Pipeline Projects
Energy Year | Project Qty | Total Capacity (KW dc) | Project Qty | Total Capacity (KW dc) | Project Qty | Total Capacity (KW dc)
EY14 | 5 | 24049.45 | 9 | 55880 | 14 | 79929.45
EY15 | 1 | 8445.58 | 10 | 71061 | 11 | 79506.58
EY16 | 0 | 0 | 10 | 71806 | 10 | 71806
Totals | 6 | 32495.03 | 29 | 198747 | 35 | 231242.03
Note: The above table provides the SRP project status as of the report date. This information is a snapshot of the program activity as of the report date. Changes to the project status or system size that may be under various stages of review are not reported here until the changes are accepted and the information is entered into the SRP Program database.

## Project List
BPU_APP_ID | Technology | Last Name | Company Name | System Size | Customer Type | TPO | Install City | Install Zip | County | Installer | Electric Utility | Grid | Subsection | Energy Yr | EDC Pgm | Status | Accepted Date | QC/QA Sel Dt | Sent to GATS | Complete Date
REIPNR-05109 | SREC Solar | BRIDGE | CONNECTIV VINELAND SOLAR, LLC | 2339.96 | Commercial |  | VINELAND | 08360 | 20 | SUN POWER | Conectiv | Yes |  |  | NONE | Complete | 09/04/2009 | 09/16/2009 | 12/17/2009 | 12/17/2009
REIPNR-06015 | SREC Solar | BRIDGE | CONECTIV VINELAND SOLAR, LLC | 1764.12 | Commercial |  | VINELAND | 08360 | 20 | SUNPOWER CORPORATION | Conectiv | Yes |  |  | NONE | Complete | 12/17/2009 | 02/05/2010 | 03/19/2010 | 03/19/2010
REIPNR-06893 | SREC Solar | JOYCE | PSEG NUCLEAR LLC., PROCESSING CTR | 239.12 | Commercial |  | HANCOCKS BRIDGE | 08035 | 14 | GEOGENIX | AC Electric | Yes |  |  | NONE | Complete | 03/25/2010 | 06/11/2010 | 09/17/2010 | 09/17/2010
REIPNR-07674 | SREC Solar | GRISOLIA | PSE&G POLE ATTACHED SOLAR 2009_09 | 17.2 | Commercial |  | WOODBRIDGE | 07095 | 11 | RIGGS DISTILLER & CO INC | PSE&G | Yes | EDC |  | PAS | Complete | 06/24/2010 | 09/30/2009 |  | 02/25/2014
REIPNR-07675 | SREC Solar | GRISOLIA | PSE&G POLE ATTACHED SOLAR 2009_10 | 16 | Commercial |  | METUCHEN | 08840 | 11 | RIGGS DISTILLER & CO INC | PSE&G | Yes | EDC |  | PAS | Complete | 06/24/2010 | 10/31/2009 |  | 02/25/2014
REIPNR-07676 | SREC Solar | GRISOLIA | PSE&G POLE ATTACHED SOLAR 2009_11 | 296.8 | Commercial |  | NEW BRUNSWICK CITY | 08901 | 11 | RIGGS DISTILLER & CO INC | PSE&G | Yes | EDC |  | PAS | Complete | 06/24/2010 | 11/30/2009 |  | 02/25/2014
REIPNR-07677 | SREC Solar | GRISOLIA | PSE&G POLE ATTACHED SOLAR 2009_12 | 700.6 | Commercial |  | EDISON | 08817 | 11 | RIGGS DISTILLER & CO INC | PSE&G | Yes | EDC |  | PAS | Complete | 06/24/2010 | 12/31/2009 |  | 02/25/2014
REIPNR-07678 | SREC Solar | GRISOLIA | PSE&G POLE ATTACHED SOLAR 2010_01 | 578.85 | Commercial |  | PISCATAWAY TWP | 08854 | 11 | RIGGS DISTILLER & CO INC | PSE&G | Yes | EDC |  | PAS | Complete | 06/24/2010 | 01/31/2010 |  | 02/25/2014
REIPNR-07679 | SREC Solar | GRISOLIA | PSE&G POLE ATTACHED SOLAR 2010_02 | 511.18 | Commercial |  | CHERRY HILL | 08104 | 14 | RIGGS DISTILLER & CO INC | PSE&G | Yes | EDC |  | PAS | Complete | 06/24/2010 | 02/28/2010 |  | 02/25/2014
REIPNR-07680 | SREC Solar | GRISOLIA | PSE&G POLE ATTACHED SOLAR 2010_03 | 689.91 | Commercial |  | PENNSAUKEN TWP | 08110 | 14 | RIGGS DISTILLER & CO INC | PSE&G | Yes | EDC |  | PAS | Complete | 06/24/2010 | 03/31/2010 |  | 02/25/2014
REIPNR-07681 | SREC Solar | GRISOLIA | PSE&G POLE ATTACHED SOLAR 2010_04 | 1562 | Commercial |  | CAMDEN CITY | 08105 | 14 | RIGGS DISTILLER & CO INC | PSE&G | Yes | EDC |  | PAS | Complete | 06/24/2010 | 04/30/2010 |  | 02/25/2014
REIPNR-07682 | SREC Solar | GRISOLIA | PSE&G POLE ATTACHED SOLAR 2010_05 | 1259.3 | Commercial |  | HAMILTON TWP | 08610 | 12 | RIGGS DISTILLER & CO INC | PSE&G | Yes | EDC |  | PAS | Complete | 06/24/2010 | 05/31/2010 |  | 02/25/2014
REIPNR-07683 | SREC Solar | GRISOLIA | PSE&G POLE ATTACHED SOLAR 2010_06 | 1578.98 | Commercial |  | DEPTFORD | 08096 | 15 | RIGGS DISTILLER & CO INC | PSE&G | Yes | EDC |  | PAS | Complete | 06/24/2010 | 06/30/2010 |  | 02/25/2014
REIPNR-07684 | SREC Solar | GRISOLIA | PSE&G POLE ATTACHED SOLAR 2010_07 | 1161.18 | Commercial |  | HILLSBOROUGH TWP | 08844 | 5 | RIGGS DISTILLER & CO INC | PSE&G | Yes | EDC |  | PAS | Complete | 06/24/2010 | 07/31/2010 |  | 02/25/2014
REIPNR-07685 | SREC Solar | GRISOLIA | PSE&G POLE ATTACHED SOLAR 2010_08 | 1242.14 | Commercial |  | FRANKLIN TWP | 08030 | 14 | RIGGS DISTILLER & CO INC | PSE&G | Yes | EDC |  | PAS | Complete | 06/24/2010 | 08/31/2010 |  | 02/25/2014
REIPNR-07686 | SREC Solar | GRISOLIA | PSE&G POLE ATTACHED SOLAR 2010_09 | 1147.705 | Commercial |  | EDISON | 08820 | 11 | RIGGS DISTILLER & CO INC | PSE&G | Yes | EDC |  | PAS | Complete | 06/24/2010 | 09/30/2010 |  | 02/25/2014
REIPNR-07687 | SREC Solar | ONDISHIN | PSE&G POLE ATTACHED SOLAR 2010_10 | 1569.655 | Commercial |  | PISCATAWAY | 08854 | 11 | RIGGS DISTILLER & CO INC | PSE&G | Yes | EDC |  | PAS | Complete | 06/24/2010 | 10/31/2010 |  | 02/25/2014
REIPNR-07688 | SREC Solar | ONDISHIN | PSE&G POLE ATTACHED SOLAR 2010_11 | 1286.685 | Commercial |  | WOODBRIDGE | 08830 | 11 | RIGGS DISTILLER & CO INC | PSE&G | Yes | EDC |  | PAS | Complete | 06/24/2010 | 11/30/2010 |  | 02/25/2014
REIPNR-07689 | SREC Solar | SWAN | PSE&G POLE ATTACHED SOLAR 2010_12 | 1109.085 | Commercial |  | NEWARK CITY | 07114 | 9 | RIGGS DISTILLER & CO INC | PSE&G | Yes | EDC |  | PAS | Complete | 06/24/2010 | 12/31/2010 |  | 02/25/2014
REIPNR-07690 | SREC Solar | SWAN | PSE&G POLE ATTACHED SOLAR 2011_01 | 975.515 | Commercial |  | NEWARK CITY | 07114 | 9 | RIGGS DISTILLER & CO INC | PSE&G | Yes | EDC |  | PAS | Complete | 06/24/2010 | 01/31/2011 |  | 02/25/2014
REIPNR-07691 | SREC Solar | SWAN | PSE&G POLE ATTACHED SOLAR 2011_02 | 1249.56 | Commercial |  | NEWARK CITY | 07105 | 9 | RIGGS DISTILLER & CO INC | PSE&G | Yes | EDC |  | PAS | Complete | 06/24/2010 | 02/28/2011 |  | 02/25/2014
REIPNR-07692 | SREC Solar | GRISOLIA | PSE&G POLE ATTACHED SOLAR 2011_03 | 1337.625 | Commercial |  | NEWARK | 08550 | 12 | RIGGS DISTILLER & CO INC | PSE&G | Yes | EDC |  | PAS | Complete | 06/24/2010 | 03/31/2011 |  | 02/25/2014
REIPNR-07693 | SREC Solar | GRISOLIA | PSE&G POLE ATTACHED SOLAR 2011_04 | 917.865 | Commercial |  | NEWARK CITY | 07114 | 9 | RIGGS DISTILLER & CO INC | PSE&G | Yes | EDC |  | PAS | Complete | 06/24/2010 | 04/30/2011 |  | 02/25/2014
REIPNR-07694 | SREC Solar | SWAN | PSE&G POLE ATTACHED SOLAR 2011_05 | 732.3 | Commercial |  | PATERSON CITY | 07501 | 6 | RIGGS DISTILLER & CO INC | PSE&G | Yes | EDC |  | PAS | Complete | 06/24/2010 | 05/31/2011 |  | 02/25/2014
REIPNR-07695 | SREC Solar | GRISOLIA | PSE&G POLE ATTACHED SOLAR 2011_06 | 913.3 | Commercial |  | PATERSON CITY | 07501 | 6 | RIGGS DISTILLER & CO INC | PSE&G | Yes | EDC |  | PAS | Complete | 06/24/2010 | 06/30/2011 |  | 02/25/2014
REIPNR-07696 | SREC Solar | GRISOLIA | PSE&G POLE ATTACHED SOLAR 2011_07 | 655.775 | Commercial |  | NEWARK | 07102 | 9 | RIGGS DISTILLER & CO INC | PSE&G | Yes | EDC |  | PAS | Complete | 06/24/2010 | 07/31/2011 |  | 02/25/2014
REIPNR-07697 | SREC Solar | GRISOLIA | PSE&G POLE ATTACHED SOLAR 2011_08 | 689.295 | Commercial |  | JERSEY CITY | 07306 | 8 | RIGGS DISTILLER & CO INC | PSE&G | Yes | EDC |  | PAS | Complete | 06/24/2010 | 08/31/2011 |  | 02/25/2014
REIPNR-07698 | SREC Solar | GRISOLIA | PSE&G POLE ATTACHED SOLAR 2011_09 | 434.4 | Commercial |  | CLIFTON CITY | 07013 | 6 | RIGGS DISTILLER & CO INC | PSE&G | Yes | EDC |  | PAS | Complete | 06/24/2010 | 09/30/2011 |  | 02/25/2014
REIPNR-07699 | SREC Solar | GRISOLIA | PSE&G POLE ATTACHED SOLAR 2011_10 | 1151.45 | Commercial |  | JERSEY CITY | 07306 | 8 | RIGGS DISTILLER & CO INC | PSE&G | Yes | EDC |  | PAS | Complete | 06/24/2010 | 10/31/2011 |  | 02/25/2014
REIPNR-07700 | SREC Solar | GRISOLIA | PSE&G POLE ATTACHED SOLAR 2011_11 | 519.775 | Commercial |  | JERSEY CITY | 07306 | 8 | RIGGS DISTILLER & CO INC | PSE&G | Yes | EDC |  | PAS | Complete | 06/24/2010 | 11/30/2011 |  | 02/25/2014
REIPNR-07701 | SREC Solar | GRISOLIA | PSE&G POLE ATTACHED SOLAR 2011_12 | 972.955 | Commercial |  | TRENTON CITY | 08608 | 12 | RIGGS DISTILLER & CO INC | PSE&G | Yes | EDC |  | PAS | Complete | 06/24/2010 | 12/31/2011 |  | 02/25/2014
REIPNR-07702 | SREC Solar | GRISOLIA | PSE&G POLE ATTACHED 2012-01 | 912.71 | Commercial |  | SECAUCUS | 07094 | 8 | RIGGS DISTILLER & CO INC | PSE&G | Yes | EDC |  | PAS | Complete | 06/24/2010 | 01/31/2012 |  | 02/25/2014
REIPNR-07703 | SREC Solar | GRISOLIA | PSE&G POLE ATTACHED 2012-02 | 700.34 | Commercial |  | CLIFTON CITY | 07013 | 6 | RIGGS DISTILLER & CO INC | PSE&G | Yes | EDC |  | PAS | Complete | 06/24/2010 | 02/29/2012 |  | 02/25/2014
REIPNR-08571 | SREC Solar | WILLIAMS | BARRINGER HIGH SCHOOL, NEWWARK | 646.8 | Non Profit |  | NEWARK | 07104 | 9 | MERCURY SOLAR SYSTEMS - PORT CHESTER | PSE&G | Yes | EDC |  | S4A1 | Complete | 09/15/2010 | 10/15/2010 | 12/14/2010 | 12/14/2010
REIPNR-08580 | SREC Solar | GRISOLIA | PSE&G CENTRAL DIVISION | 916.28 | Commercial |  | SOMERSET | 08873 | 5 | SOLIS PARTNERS, LLC | PSE&G | Yes | EDC |  | S4A1 | Complete | 09/15/2010 | 11/09/2010 | 01/10/2011 | 01/10/2011
REIPNR-08608 | SREC Solar | GRISOLLA | PSE&G BRUNSWICK | 1264.08 | Commercial |  | TRENTON | 08618 | 12 | NVT LICENSES, LLC | Not Known | Yes | EDC |  | S4A1 | Complete | 09/15/2010 | 11/05/2010 | 12/22/2010 | 12/22/2010
REIPNR-08657 | SREC Solar | WILLIAMS | NEWARK PUBLIC SCHOOLS | 501.39 | School Other |  | NEWARK | 07103 | 9 | LB ELECTRIC CO. LLC | PSE&G | Yes | EDC |  | S4A1 | Complete | 09/15/2010 | 12/30/2010 | 05/03/2011 | 05/03/2011
REIPNR-08991 | SREC Solar | GRISOLLA | PUBLIC SERVICE ELECTRIC AND GAS | 3196.93 | Commercial |  | LINDEN | 07036 | 10 | ADVANCED SOLAR PRODUCTS FLEMINGTON | PSE&G | Yes | EDC |  | S4A1 | Complete | 10/06/2010 | 12/29/2010 | 03/10/2011 | 03/10/2011
REIPNR-09011 | SREC Solar | WILLIAMS | PARK ELEMENTARY SCHOOL | 510.48 | School Public K-12 |  | NEWARK | 07104 | 9 | MERCURY SOLAR SYSTEMS | PSE&G | Yes | EDC |  | S4A1 | Complete | 10/06/2010 | 10/28/2010 | 05/11/2011 | 05/11/2011
REIPNR-09296 | SREC Solar | GRISOLIA | PUBLIC SERVICE ELECTRIC & GAS | 2017.596 | Commercial |  | EDISON | 08817 | 11 | J. FLETCHER CREAMER & SON | PSE&G | Yes | EDC |  | S4A1 | Complete | 10/19/2010 | 12/15/2010 | 04/28/2011 | 04/28/2011
REIPNR-09377 | SREC Solar | ADLER | ADLER DEVELOPMENT | 907.632 | Commercial |  | WOODBRIDGE | 08512 | 11 | ADVANCED GREEN TECHNOLOGIES | PSE&G | Yes |  |  | NONE | Complete | 10/26/2010 | 03/15/2011 | 03/24/2011 | 03/24/2011
REIPNR-09779 | SREC Solar | HORTON | WEA TEXAS BAYONNE, LP | 1746.36 | Commercial |  | BAYONNE | 07002 | 8 | ADVANCED SOLAR PRODUCTS FLEMINGTON | PSE&G | Yes | EDC |  | S4A1 | Complete | 11/20/2010 | 01/03/2011 | 03/08/2011 | 03/08/2011
REIPNR-10398 | SREC Solar | SCHNECK | PARADISE SOLAR URBAN RENEWAL | 6158.88 | Commercial |  | WEST DEPTFORD | 08066 | 15 | AMERICAN CAPITAL ENERGY | PSE&G | Yes |  |  | NONE | Complete | 11/22/2010 | 04/06/2011 | 05/11/2011 | 05/11/2011
REIPNR-10399 | SREC Solar | TESSUM | PILESGROVE SOLAR, LLC CIRCUIT #1 | 9947.94 | Commercial |  | PILESGROVE | 08098 | 16 | RMT, INC | AC Electric | Yes |  |  | NONE | Complete | 11/22/2010 | 10/31/2011 | 12/09/2011 | 12/09/2011
REIPNR-10400 | SREC Solar | WILLIAMS | CAMDEN STREET SCHOOL | 913.92 | School Public K-12 |  | NEWARK | 07103 | 9 | ALPHA TECHNOLOGIES | PSE&G | Yes | EDC |  | S4A1 | Complete | 11/22/2010 | 06/14/2011 | 07/22/2011 | 07/22/2011
REIPNR-10766 | SREC Solar | GRISOLIA | PSE&G YARDVILLE | 4302.36 | Commercial |  | HAMILTON | 08610 | 12 | AMERICAN CAPITAL ENERGY | PSE&G | Yes | EDC |  | S4A1 | Complete | 12/20/2010 | 02/08/2011 | 04/05/2011 | 04/05/2011
REIPNR-10767 | SREC Solar | GRISOLIA | PSE&G-EDISON TRAINING CENTER | 711.9 | Commercial |  | EDISON | 08837 | 11 | HENKELS AND MC COY INC. | PSE&G | Yes | EDC |  | S4A1 | Complete | 12/20/2010 | 12/29/2010 | 03/23/2011 | 03/23/2011
REIPNR-10994 | SREC Solar | CONNELLY | MATRIX INDUSTRIAL | 1170.675 | Commercial |  | PERTH AMBOY | 08861 | 11 | ENXCO DEVELOPMENT CORPORATION | PSE&G | Yes | EDC |  | S4A1 | Complete | 01/03/2011 | 01/18/2011 | 03/09/2011 | 03/09/2011
REIPNR-11342 | SREC Solar | CONNELLY | MATRIX INDUSTRIAL A LLC | 1687.95 | Commercial |  | PERTH AMBOY | 08861 | 11 | ENXCO DEVELOPMENT CORPORATION | PSE&G | Yes | EDC |  | S4A1 | Complete | 01/24/2011 | 01/25/2011 | 03/25/2011 | 03/25/2011
REIPNR-12047 | SREC Solar | ADLER | ADLER DEVELOPMENT | 578.16 | Commercial |  | CRANBURY | 08512 | 11 | ADVANCED GREEN TECHNOLOGIES | PSE&G | Yes |  |  | NONE | Complete | 02/28/2011 | 08/22/2011 | 08/30/2011 | 08/30/2011
SRP01265 | SREC Solar | CONNELLY | MATRIX STULTS RD ASSOCIATES LLC | 2980.74 | Commercial |  | DAYTON | 08810 | 11 | PRO-TECH ENERGY SOLUTIONS | PSE&G | Yes | EDC |  | S4A1 | Complete | 03/15/2011 | 06/13/2011 | 08/05/2011 | 08/05/2011
SRP01361 | SREC Solar | HAGAN | KESSLER INDUSTRIES INC. | 638.275 | Commercial |  | WOODBRIDGE | 07095 | 11 | SPG SOLAR INC. | PSE&G | Yes |  |  | NONE | Complete | 03/28/2011 | 10/04/2011 | 01/11/2012 | 01/11/2012
SRP01541 | SREC Solar | RECA | RIDER UNIVERSITY | 739.2 | Commercial |  | LAWRENCEVILLE | 08648 | 12 | ALTERIS RENEWABLES | PSE&G | Yes | EDC |  | S4A1 | Complete | 04/04/2011 | 11/14/2011 | 01/19/2012 | 01/19/2012
SRP01665 | SREC Solar | TURNURE | SYNCARPHA ALETHEA I LLC | 3010.35 | Commercial |  | EASTAMPTON | 08060 | 13 | SIEMENS ENERGY INC. | PSE&G | Yes |  |  | NONE | Complete | 04/04/2011 | 11/30/2011 | 01/13/2012 | 01/13/2012
SRP01888 | SREC Solar | SANDEEN | NFI SOLAR | 2000.32 | Farm |  | VINELAND | 08360 | 20 | PRINCETON SOLAR SOLUTIONS | Vineland Muni Elec | Yes |  |  | NONE | Complete | 04/11/2011 | 09/14/2011 | 10/26/2011 | 10/26/2011
SRP02500 | SREC Solar | LICHTIN | CLEANLIGHT ENERGY, LLC | 2936.64 | Commercial |  | MOUNT LAUREL | 07828 | 3 | PFISTER MAINTENANCE, INC. | PSE&G | Yes |  |  | NONE | Complete | 05/11/2011 | 12/15/2011 | 01/17/2012 | 01/17/2012
SRP02587 | SREC Solar | MCKISSACK | NJ OAK SOLAR, LLC | 12502 | Commercial |  | FAIRFIELD TWP. | 08302 | 20 | THE RYAN COMPANY, INC | AC Electric | Yes |  |  | NONE | Complete | 05/17/2011 | 01/09/2012 | 02/09/2012 | 02/09/2012
SRP02588 | SREC Solar | TRIPOLI | PPL RENEWABLE ENERGY, LLC | 2677.454 | Commercial |  | PHILLIPSBURG | 08865 | 2 | MILLENNIUM BUILDERS INC. | JCP&L | Yes |  |  | NONE | Complete | 05/17/2011 | 05/16/2012 | 06/11/2012 | 06/11/2012
SRP03209 | SREC Solar | MANGINO | VILLAGE AT MANALAPAN SOLAR LLC | 3588.2 | Commercial |  | MANALAPAN | 07726 | 17 | MERCURY SOLAR SYSTEMS - PORT CHESTER | JCP&L | Yes |  |  | NONE | Complete | 06/07/2011 | 02/07/2012 | 02/28/2012 | 02/28/2012
SRP03305 | SREC Solar | GRISOLIA | PSE&G | 733.67 | Commercial |  | CLIFTON | 07011 | 6 | ADEMA TECHNOLOGIES II | PSE&G | Yes | EDC |  | S4A1 | Complete | 06/13/2011 | 07/18/2012 | 08/02/2012 | 08/02/2012
SRP04810 | SREC Solar | GARB | HARTZ SOLAR HAMILTON, LLC | 4509.12 | Commercial |  | HAMILTON | 08620 | 12 | RMT, INC | PSE&G | Yes |  |  | NONE | Complete | 08/11/2011 | 01/24/2012 | 02/10/2012 | 02/10/2012
SRP04811 | SREC Solar | GARB | HARTZ SOLAR HAMILTON, L.L.C | 3945.48 | Commercial |  | HAMILTON | 08620 | 12 | RMT, INC | PSE&G | Yes |  |  | NONE | Complete | 08/11/2011 | 01/24/2012 | 02/10/2012 | 02/10/2012
SRP04958 | SREC Solar | GRISOLIA | PSE&G | 1050.92 | Commercial |  | HACKENSACK | 07601 | 7 | J. FLETCHER CREAMER & SON | PSE&G | Yes | EDC |  | S4A1 | Complete | 08/23/2011 | 09/24/2013 | 10/01/2013 | 10/01/2013
SRP04962 | SREC Solar | GRISOLIA | PSEG INCORPORATED | 719.95 | Commercial |  | WEST DEPTFORD | 08086 | 15 | NVT LICENSES LLC | PSE&G | Yes | EDC |  | S4A1 | Complete | 08/23/2011 | 01/23/2012 | 03/20/2012 | 03/20/2012
SRP04965 | SREC Solar | GRISOLIA | PSE&G | 3822 | Commercial |  | BURLINGTON | 08016 | 13 | JUWI SOLAR INC. | PSE&G | Yes | EDC |  | S4A1 | Complete | 08/23/2011 | 12/20/2011 | 01/17/2012 | 01/17/2012
SRP04970 | SREC Solar | DEOBLER | FLEMINGTON SOLAR, LLC | 9364.05 | Commercial |  | FLEMINGTON | 08822 | 4 | RMT, INC | JCP&L | Yes |  |  | NONE | Complete | 08/23/2011 | 01/11/2012 | 02/07/2012 | 02/07/2012
SRP04975 | SREC Solar | DEOBLER | FRENCHTOWN I SOLAR, LLC | 3474.235 | Commercial |  | FRENCHTOWN | 08825 | 4 | RMT, INC | JCP&L | Yes |  |  | NONE | Complete | 08/23/2011 | 01/18/2012 | 03/30/2012 | 03/30/2012
SRP04978 | SREC Solar | DEOBLER | FRENCHTOWN II SOLAR, LLC | 3474.03 | Commercial |  | FRENCHTOWN | 08825 | 4 | RMT, INC | JCP&L | Yes |  |  | NONE | Complete | 08/23/2011 | 01/11/2012 | 02/07/2012 | 02/07/2012
SRP04981 | SREC Solar | DEOBLER | LEBANON SOLAR, LLC | 2316.16 | Commercial |  | GLEN GARDNER | 08826 | 4 | RMT, INC | JCP&L | Yes |  |  | NONE | Complete | 08/23/2011 | 10/28/2011 | 02/20/2012 | 02/20/2012
SRP05293 | SREC Solar | WESTHOVEN | NJR CLEAN ENERGY VENTURES CORP | 4737.6 | Commercial |  | VINELAND | 08360 | 20 | AMERICAN CAPITAL ENERGY | Vineland Muni Elec | Yes |  |  | NONE | Complete | 09/06/2011 | 01/04/2012 | 02/17/2012 | 02/17/2012
SRP05299 | SREC Solar | KAGAN | CONSTELLATION SOLAR NEW JERSEY | 3006.08 | Commercial |  | VINELAND | 08360 | 20 | RMT, INC | Vineland Muni Elec | Yes |  |  | NONE | Complete | 09/06/2011 | 12/28/2011 | 01/24/2012 | 01/24/2012
SRP05301 | SREC Solar | KAGAN | CONSTELLATION SOLAR NEW JERSEY | 4804.8 | Commercial |  | VINELAND | 08360 | 20 | RMT, INC | Vineland Muni Elec | Yes |  |  | NONE | Complete | 09/06/2011 | 12/28/2011 | 01/24/2012 | 01/24/2012
SRP05303 | SREC Solar | ADLER | ADLER DEVELOPMENT | 644.84 | Commercial |  | EDISON | 08818 | 11 | GEHRLICHER SOLAR AMERICA CORP. | PSE&G | Yes |  |  | NONE | Complete | 09/06/2011 | 10/21/2011 | 12/14/2011 | 12/14/2011
SRP05304 | SREC Solar | ADLER | ADLER DEVELOPMENT | 354.9 | Commercial |  | EDISON | 08818 | 11 | GEHRLICHER SOLAR AMERICA CORP. | PSE&G | Yes |  |  | NONE | Complete | 09/06/2011 | 03/19/2012 | 04/19/2012 | 04/19/2012
SRP05305 | SREC Solar | ADLER | ADLER DEVELOPMENT | 338 | Commercial |  | EDISON | 08818 | 11 | GEHRLICHER SOLAR AMERICA CORP. | PSE&G | Yes |  |  | NONE | Complete | 09/06/2011 | 03/19/2012 | 04/19/2012 | 04/19/2012
SRP06006 | SREC Solar | KIMBER | RE CRANBURY SOLAR 1, LLC | 5738.88 | Commercial |  | CRANBURY | 08512 | 11 | HYPOWER, INC. | PSE&G | Yes |  |  | NONE | Complete | 10/10/2011 | 11/17/2011 | 12/09/2011 | 12/09/2011
SRP06270 | SREC Solar | SANDEEN | NFI SOLAR | 1028.16 | Commercial |  | VINELAND | 08360 | 20 | PRO-TECH ENERGY SOLUTIONS | Vineland Muni Elec | Yes |  |  | NONE | Complete | 10/17/2011 | 11/28/2011 | 01/11/2012 | 01/11/2012
SRP06345 | SREC Solar | SOMERS | CORNERSTONE POWER VINELAND I LLC | 3714.48 | Commercial |  | VINELAND | 08520 | 12 | WTEC | Vineland Muni Elec | Yes |  |  | NONE | Complete | 10/24/2011 | 04/05/2012 | 05/09/2012 | 05/09/2012
SRP06491 | SREC Solar | VISCEGLIA | FERNWOOD 45 ASSOCIATES LP | 2223.648 | Commercial |  | EDISON | 08818 | 11 | ADVANCED SOLAR PRODUCTS FLEMINGTON | PSE&G | Yes | EDC |  | S4A1 | Complete | 11/01/2011 | 01/23/2012 | 03/20/2012 | 03/20/2012
SRP06783 | SREC Solar | WAGNER | NERC MIDDLESEX SOLAR I LLC | 4303.44 | Commercial |  | EAST BRUNSWICK | 08816 | 11 | NEWKIRK ELECTRICAL ASSOCIATES | PSE&G | Yes |  |  | NONE | Complete | 11/08/2011 | 09/26/2012 | 11/02/2012 | 11/02/2012
SRP06921 | SREC Solar | RAGER | TINTON FALLS SOLAR FARM LLC. | 19880.56 | Commercial |  | TINTON FALLS | 07724 | 17 | UNITY ELECTRIC LLC | JCP&L | Yes | t |  | NONE | Complete | 11/14/2011 | 11/28/2012 | 10/30/2013 | 10/30/2013
SRP07045 | SREC Solar | PYSE | KEPS LANDHOLDINGS, LLC | 5001.945 | Commercial |  | MEDFORD | 08055 | 13 | CONSTELLATION ENERGY | PSE&G | Yes |  |  | NONE | Complete | 11/21/2011 | 01/26/2012 | 02/17/2012 | 02/17/2012
SRP07053 | SREC Solar | MCCANN | COMMUNITY FOODBANK OF NJ | 1073.41 | Non Profit |  | HILLSIDE | 07205 | 10 | MERCURY SOLAR SYSTEMS - PORT CHESTER | PSE&G | Yes | EDC |  | S4A1 | Complete | 11/21/2011 | 11/19/2012 | 12/10/2012 | 12/10/2012
SRP07242 | SREC Solar | TESSEM | PILESGROVE SOLAR, LLC CIRCUIT #2 | 9963.145 | Commercial |  | PILESGROVE | 08098 | 16 | RMT, INC | AC Electric | Yes |  |  | NONE | Complete | 11/22/2010 | 10/31/2011 | 12/09/2011 | 12/09/2011
SRP07331 | SREC Solar | WALKER | GRANITE SOUTH BRUNSWICK, LLC | 2970.24 | Commercial |  | DAYTON | 08810 | 11 | PRO-TECH ENERGY SOLUTIONS | PSE&G | Yes | EDC |  | S4A1 | Complete | 12/05/2011 | 04/04/2012 | 04/26/2012 | 04/26/2012
SRP07611 | SREC Solar | LEVY | NEW JERSEY MEADOWLANDS COMMISS | 3001.44 | Government Facility |  | KEARNY | 07032 | 8 | SUNDURANCE ENERGY | PSE&G | Yes | EDC |  | S4A1 | Complete | 12/19/2011 | 02/08/2012 | 05/15/2012 | 05/15/2012
SRP07994 | SREC Solar | WENZEL | SOUTH JERSEY GAS | 2517.32 | Commercial |  | EGG HARBOR TWP | 08234 | 19 | DCO ENERGY, LLC | AC Electric | Yes |  |  | NONE | Complete | 01/03/2012 | 03/15/2012 | 04/19/2012 | 04/19/2012
SRP10203 | SREC Solar | SWAN | PSE&G POLE ATTACHED 2012-03 | 1091.78 | Commercial |  | EAST ORANGE CITY | 07017 | 9 | RIGGS DISTILLER & CO INC | PSE&G | Yes | EDC |  | PAS | Complete | 04/19/2012 | 03/31/2012 |  | 02/25/2014
SRP10206 | SREC Solar | SWAN | PSE&G POLE ATTACHED 2012-04 | 851.94 | Commercial |  | MONTCLAIR TWP | 07042 | 9 | RIGGS DISTILLER & CO INC | PSE&G | Yes | EDC |  | PAS | Complete | 04/19/2012 | 04/30/2012 |  | 02/25/2014
SRP10227 | SREC Solar | SWAN | PSE&G POLE ATTACHED 2012-05 | 603.235 | Commercial |  | CAMDEN CITY | 08105 | 14 | RIGGS DISTILLER & CO INC | PSE&G | Yes | EDC |  | PAS | Complete | 04/20/2012 | 05/31/2012 |  | 02/25/2014
SRP10228 | SREC Solar | SWAN | PSE&G POLE ATTACHED 2012-06 | 1056.095 | Commercial |  | JERSEY CITY | 07306 | 8 | RIGGS DISTILLER & CO INC | PSE&G | Yes | EDC |  | PAS | Complete | 04/20/2012 | 06/30/2012 |  | 02/25/2014
SRP10233 | SREC Solar | SWAN | PSE&G POLE ATTACHED 2012-07 | 767.925 | Commercial |  | ELIZABETH CITY | 07202 | 10 | RIGGS DISTILLER & CO INC | PSE&G | Yes | EDC |  | PAS | Complete | 04/20/2012 | 07/31/2012 |  | 02/25/2014
SRP10238 | SREC Solar | SWAN | PSE&G POLE ATTACHED 2012-08 | 1074.96 | Commercial |  | SOUTH PLAINFIELD BORO | 07080 | 11 | RIGGS DISTILLER & CO INC | PSE&G | Yes | EDC |  | PAS | Complete | 04/20/2012 | 08/30/2012 |  | 02/25/2014
SRP10241 | SREC Solar | SWAN | PSE&G POLE ATTACHED 2012-09 | 869.17 | Commercial |  | EDISON TWP | 08837 | 11 | RIGGS DISTILLER & CO INC | PSE&G | Yes | EDC |  | PAS | Complete | 04/20/2012 | 09/28/2012 |  | 02/25/2014
SRP10242 | SREC Solar | SWAN | PSE&G POLE ATTACHED 2012-10 | 1006.525 | Commercial |  | NEWARK CITY | 07106 | 9 | RIGGS DISTILLER & CO INC | PSE&G | Yes | EDC |  | PAS | Complete | 04/20/2012 | 10/26/2012 |  | 02/25/2014
SRP10243 | SREC Solar | SWAN | PSE&G POLE ATTACHED 2012-11 | 166.52 | Commercial |  | BLOOMFIELD TWP. | 07003 | 9 | RIGGS DISTILLER & CO INC | PSE&G | Yes | EDC |  | PAS | Complete | 04/20/2012 | 11/29/2012 |  | 02/25/2014
SRP10244 | SREC Solar | SWAN | PSE&G POLE ATTACHED 2012-12 | 591.535 | Commercial |  | HAMILTON TWP. | 08619 | 12 | RIGGS DISTILLER & CO INC | PSE&G | Yes | EDC |  | PAS | Complete | 04/20/2012 | 12/27/2012 |  | 02/25/2014
SRP10303 | SREC Solar | PYSE | KEPS LANDHOLDINGS LLC | 6692.62 | Commercial |  | MEDFORD | 08055 | 13 | GEHRLICHER SOLAR AMERICA CORP. | PSE&G | Yes | s |  | NONE | Complete | 04/30/2012 | 10/11/2012 | 06/18/2013 | 06/18/2013
SRP10928 | SREC Solar | CHOW | SPS PROJECT 1, LLC | 2299.08 | Commercial |  | PITTSTOWN | 08867 | 4 | ROWE ELECTRIC INC | JCP&L | Yes | s |  | NONE | Complete | 05/29/2012 | 12/23/2013 | 12/27/2013 | 12/27/2013
SRP11256 | SREC Solar | KATZ | MILLENIUM DEVELOPMENT LIMITED LLC | 9799.2 | Commercial |  | FLEMINGTON | 08822 | 4 | RENEWABLE POWER | JCP&L | Yes |  |  | NONE | Accepted | 06/11/2012
SRP11625 | SREC Solar | LUI | NORTH AMERICA SOLAR CORP | 8578.5 | Commercial |  | SPRINGFIELD | 08505 | 13 | BLUE SKY TECHNOLOGIES USA | PSE&G | Yes |  |  | NONE | Accepted | 06/25/2012
SRP14920 | SREC Solar | NEUMAN | GREENWICH SOLAR W2-091 LLC | 11440.8 | Commercial |  | GREENWICH | 08886 | 2 | EFFISOLAR DEVELOPMENT LLC | JCP&L | Yes |  |  | NONE | Accepted | 11/19/2012
SRP14921 | SREC Solar | NEUMAN | FRANKLIN SOLAR W3-077 LLC | 13283.2 | Commercial |  | FRANKLIN | 07882 | 2 | EFFISOLAR DEVELOPMENT LLC | JCP&L | Yes |  |  | NONE | Accepted | 11/19/2012
SRP16560 | SREC Solar | SWAN | PSE&G POLE ATTACHED 2013-01 | 847.66 | Commercial |  | RAHWAY CITY | 07065 | 10 | RIGGS DISTILLER & CO INC | PSE&G | Yes | EDC |  | PAS | Complete | 01/25/2013 | 01/25/2013 |  | 02/25/2014
SRP16562 | SREC Solar | SWAN | PSE&G POLE ATTACHED 2013-02 | 751.84 | Commercial |  | CAMDEN CITY | 08105 | 14 | RIGGS DISTILLER & CO INC | PSE&G | Yes | EDC |  | PAS | Complete | 01/25/2013 | 02/22/2013 |  | 02/25/2014
SRP16563 | SREC Solar | SWAN | PSE&G POLE ATTACHED 2013-03 | 697.22 | Commercial |  | HAMILTON TWP | 08610 | 12 | RIGGS DISTILLER & CO INC | PSE&G | Yes | EDC |  | PAS | Complete | 01/25/2013 | 03/29/2013 |  | 02/25/2014
SRP16566 | SREC Solar | SWAN | PSE&G POLE ATTACHED 2013-04 | 670.525 | Commercial |  | TRENTON CITY | 08609 | 12 | RIGGS DISTILLER & CO INC | PSE&G | Yes | EDC |  | PAS | Complete | 01/25/2013 | 04/26/2013 |  | 02/25/2014
SRP16567 | SREC Solar | SWAN | PSE&G POLE ATTACHED 2013-05 | 335.715 | Commercial |  | WESTFIELD TOWN | 07090 | 10 | RIGGS DISTILLER & CO INC | PSE&G | Yes | EDC |  | PAS | Complete | 01/25/2013 | 05/28/2013 |  | 02/25/2014
SRP16568 | SREC Solar | SWAN | PSE&G POLE ATTACHED 2013-06 | 74.825 | Commercial |  | WOODBRIDGE TWP | 07067 | 10 | RIGGS DISTILLER & CO INC | PSE&G | Yes | EDC |  | PAS | Complete | 01/25/2013 | 06/28/2013 |  | 02/25/2014
SRP18427 | SREC Solar | GRISOLIA | PSE&G | 1072.305 | Commercial |  | MOORESTOWN | 08057 | 13 | VANGUARD ENERGY PARTNERS, LLC | PSE&G | Yes | EDC |  | S4A1 | Complete | 04/29/2013 | 04/09/2014 | 04/10/2014 | 04/10/2014
SRP18815 | SREC Solar | ROGERS | CORNERSTONE POWER HOLMDEL, LLC | 3696 | Commercial |  | HOLMDEL | 07733 | 17 | SWINERTON BUILDERS | JCP&L | Yes | s |  | NONE | Complete | 05/15/2013 | 12/02/2013 | 03/18/2014 | 03/18/2014
SRP19365 | SREC Solar | SWAN | PSE&G POLE ATTACHED 2013-07 | 30.145 | Commercial |  | ELIZABETH CITY | 07201 | 10 | RIGGS DISTILLER & CO INC | PSE&G | Yes | EDC |  | PAS | Complete | 06/13/2013 | 07/26/2013 |  | 02/25/2014
SRP19367 | SREC Solar | SWAN | PSE&G POLE ATTACHED 2013-08 | 49.085 | Commercial |  | WESTFIELD TWP. | 07090 | 10 | RIGGS DISTILLER & CO INC | PSE&G | Yes | EDC |  | PAS | Complete | 06/13/2013 | 08/30/2013 |  | 02/25/2014
SRP19368 | SREC Solar | SWAN | PSE&G POLE ATTACHED 2013-09 | 0 | Commercial |  | WOODBRIDGE TWP. | 07067 | 10 | RIGGS DISTILLER & CO INC | PSE&G | Yes | EDC |  | PAS | Complete | 06/13/2013 | 09/27/2013 |  | 02/25/2014
SRP19369 | SREC Solar | SWAN | PSE&G POLE ATTACHED 2013-10 | 0 | Commercial |  | WOODBRIDGE TWP | 07067 | 10 | RIGGS DISTILLER & CO INC | PSE&G | Yes | EDC |  | PAS | Complete | 06/13/2013 | 10/25/2013 |  | 02/25/2014
SRP19371 | SREC Solar | SWAN | PSE&G POLE ATTACHED 2013-11 | 0 | Commercial |  | CAMDEN CITY | 08105 | 14 | RIGGS DISTILLER & CO INC | PSE&G | Yes | EDC |  | PAS | Complete | 06/13/2013 | 11/29/2013 |  | 02/25/2014
SRP19373 | SREC Solar | SWAN | PSE&G POLE ATTACHED 2013-12 | 63.98 | Commercial |  | CAMDEN CITY | 08105 | 14 | RIGGS DISTILLER & CO INC | PSE&G | Yes | EDC |  | PAS | Complete | 06/13/2013 | 12/27/2013 |  | 02/27/2014
SRP21092 | SREC Solar | MEURER | MEURER DEVELOPMENT, LLC | 5416 | Commercial |  | FLEMINGTON | 08822 | 4 | GREEN POWER ENERGY LLC | JCP&L | Yes | q | EY15 | NONE | Accepted | 11/22/2013
SRP21202 | SREC Solar | WILLIAMS | POLLUTION CONTROL WARREN COUNT | 1173.92 | Government Facility |  | OXFORD | 07863 | 2 | DCO ENERGY, LLC | JCP&L | Yes | q | EY14 | NONE | Complete | 11/22/2013 | 07/16/2014 | 10/10/2014 | 10/10/2014
SRP21213 | SREC Solar | FAVORITO | PITTSGROVE SOLAR LLC | 2285.8 | Commercial |  | PITTSGROVE | 08318 | 16 | MILLER BROS. ELECTRICAL CONTRACTORS | AC Electric | Yes | q | EY14 | NONE | QC Selected | 11/22/2013 | 06/30/2014
SRP21344 | SREC Solar | NEUMAN | HOWELL W3-079 LLC | 9000 | Commercial |  | HOWELL | 07731 | 17 | EFFISOLAR DEVELOPMENT LLC | JCP&L | Yes | q | EY15 | NONE | Accepted | 11/22/2013
SRP21346 | SREC Solar | CRONIN | CROSNEST AT PARKER FARM, LLC | 6121 | Commercial |  | NORTH HANOVER TWP | 08562 | 13 | GEHRLICHER SOLAR AMERICA CORP. | JCP&L | Yes | q | EY14 | NONE | Accepted | 11/22/2013
SRP21347 | SREC Solar | PYSE | KEPS LANDHOLDINGS, LLC | 1414.82 | Commercial |  | MEDFORD | 08055 | 13 | GEHRLICHER SOLAR AMERICA CORP. | PSE&G | Yes | q | EY14 | NONE | Complete | 11/22/2013 | 01/15/2014 | 05/06/2014 | 05/06/2014
SRP21348 | SREC Solar | KAY | 206 ASSOCIATES | 9189.93 | Commercial |  | PEMBERTON TWP | 08060 | 13 | GEHRLICHER SOLAR AMERICA CORP. | PSE&G | Yes | q | EY14 | NONE | Complete | 11/22/2013 | 07/23/2014 | 10/16/2014 | 10/16/2014
SRP21349 | SREC Solar | KOTZIAS | ALETHEA SOLAR II, LLC | 3326 | Commercial |  | EAST AMWELL | 08551 | 4 | GEHRLICHER SOLAR AMERICA CORP. | JCP&L | Yes | q | EY15 | NONE | Accepted | 11/22/2013
SRP21351 | SREC Solar | WONG | ROCK SOLID REALTY (NJ) CORP | 9999 | Commercial |  | HOWELL | 07731 | 17 | PRO-TECH ENERGY SOLUTIONS | JCP&L | Yes | q | EY14 | NONE | Accepted | 11/22/2013
SRP21352 | SREC Solar | MADDONNI | PENNONI ASSOC. INC. | 5000 | Commercial |  | DEPTFORD | 08096 | 15 | SELF INSTALL | PSE&G | Yes | q | EY14 | NONE | Accepted | 11/22/2013
SRP21353 | SREC Solar | SHOTMEYER | BEAVER RUN SOLAR FARM, LLC | 9900 | Commercial |  | LAFAYETTE | 07848 | 1 | SELF INSTALL | Not Known | Yes | q | EY14 | NONE | Accepted | 11/22/2013
SRP21355 | SREC Solar | FERGUSON | GARDEN SOLAR LLC | 3500 | Commercial |  | HOLLAND TWP | 08848 | 4 | SOLUS ENERGY LLC | JCP&L | Yes | q | EY16 | NONE | Accepted | 11/22/2013
SRP21356 | SREC Solar | SKUDERA | BRICKYARD LLC | 2000 | Commercial |  | FARMINGDALE | 07727 | 17 | SELF INSTALL | JCP&L | Yes | q | EY15 | NONE | Accepted | 11/22/2013
SRP21358 | SREC Solar | CRONIN | CROSNEST AT PARKER FARM, LLC | 9100 | Commercial |  | NORTH HANOVER TWP | 08562 | 13 | COMMUNITY ENERGY SOLAR LLC | JCP&L | Yes | q | EY14 | NONE | Accepted | 11/22/2013
SRP21359 | SREC Solar | CROUSE | 166 BRAINARDS RD, LLC | 3900 | Commercial |  | HARMONY TWP | 08865 | 2 | COMMUNITY ENERGY SOLAR LLC | JCP&L | Yes | q | EY14 | NONE | Accepted | 11/22/2013
SRP21361 | SREC Solar | MAZZONI |  | 7150 | Commercial |  | BUENA VISTA TWP | 08360 | 20 | COMMUNITY ENERGY SOLAR LLC | AC Electric | Yes | q | EY16 | NONE | Accepted | 11/22/2013
SRP21362 | SREC Solar | WALLSTEN | THE ESTATE OF CARL W. WALLSTEN | 6500 | Commercial |  | UPPER FREEHOLD TWP | 08501 | 17 | COMMUNITY ENERGY SOLAR LLC | JCP&L | Yes | q | EY15 | NONE | Accepted | 11/22/2013
SRP21365 | SREC Solar | DEOBLER | FRENCHTOWN III SOLAR LLC | 9984.98 | Commercial |  | KINGWOOD TWP | 08825 | 4 | GEHRLICHER SOLAR AMERICA CORP. | JCP&L | Yes | q | EY14 | NONE | Complete | 11/22/2013 | 02/19/2014 | 04/11/2014 | 04/11/2014
SRP25244 | SREC Solar | WIEGAND | NORTHPARK SOLAR, LLC | 1700 | Commercial |  | MANALAPAN | 07726 | 17 | BAM CONSTRUCTION GROUP, LLC | JCP&L | Yes | q | EY14 | NONE | Accepted | 04/30/2014
SRP25246 | SREC Solar | WIEGAND | AUGUSTA SOLAR FARM, LLC | 3660 | Commercial |  | NEWTON | 07860 | 1 | BAM CONSTRUCTION GROUP, LLC | JCP&L | Yes | q | EY14 | NONE | Accepted | 04/30/2014
SRP25247 | SREC Solar | KHASIDY | G&S WANTAGE SOLAR LLC | 8445.58 | Commercial |  | WANTAGE | 07461 | 1 | G & S INVESTORS | JCP&L | Yes | q | EY15 | NONE | Complete | 04/30/2014 | 06/06/2014 | 07/10/2014 | 07/10/2014
SRP25248 | SREC Solar | BEERLEY | MILLSTONE SOLAR LLC | 10000 | Commercial |  | MILLSTONES TWP | 08510 | 17 | COMMUNITY ENERGY SOLAR LLC | JCP&L | Yes | q | EY16 | NONE | Accepted | 04/30/2014
SRP25256 | SREC Solar | KOTZIAS | ALETHEA SOLAR IV, LLC | 10000 | Commercial |  | RARITAN | 08551 | 4 | UNITY ELECTRIC LLC | JCP&L | Yes | q | EY15 | NONE | Accepted | 04/30/2014
SRP25258 | SREC Solar | BEERLEY | HANOVER SOLAR LLC | 6000 | Commercial |  | NORTH HANOVER TWP | 08562 | 13 | COMMUNITY ENERGY SOLAR LLC | JCP&L | Yes | q | EY15 | NONE | Accepted | 04/30/2014
SRP25259 | SREC Solar | AVNERY | LANDSOLAR LLC | 9905 | Commercial |  | FRANKFORD | 07826 | 1 | ITA | JCP&L | Yes | q | EY15 | NONE | Accepted | 04/30/2014
SRP25261 | SREC Solar | FRATUS | GARDEN SOLAR LLC | 2500 | Commercial |  | FLEMINGTON | 08822 | 4 | MILLER BROS. ELECTRICAL CONTRACTORS | JCP&L | Yes | q | EY16 | NONE | Accepted | 04/30/2014
SRP25262 | SREC Solar | NEUMAN | RARITAN SOLAR W3-029 LLC | 10000 | Commercial |  | RARITAN | 08551 | 4 | EFFISOLAR DEVELOPMENT LLC | JCP&L | Yes | q | EY16 | NONE | Final DE | 04/30/2014
SRP25265 | SREC Solar | NEUMAN | FLORENCE SOLAR W3-080 LLC | 10000 | Commercial |  | FLORENCE | 08518 | 13 | EFFISOLAR DEVELOPMENT LLC | PSE&G | Yes | q | EY16 | NONE | Accepted | 04/30/2014
SRP25266 | SREC Solar | FRATUS | GARDEN SOLAR LLC | 9999 | Commercial |  | WASHINGTON | 07882 | 2 | MILLER BROS. ELECTRICAL CONTRACTORS | JCP&L | Yes | q | EY16 | NONE | Accepted | 04/30/2014
SRP25268 | SREC Solar | NEUMAN | LUMBERTON SOLAR W2-090 LLC | 9457 | Commercial |  | LUMBERTON | 07095 | 11 | EFFISOLAR DEVELOPMENT LLC | PSE&G | Yes | q | EY15 | NONE | Accepted | 04/30/2014
SRP25270 | SREC Solar | NEUMAN | GREENWICH SOLAR W2-091 LLC | 9457 | Commercial |  | GREENWICH | 08886 | 2 | EFFISOLAR DEVELOPMENT LLC | JCP&L | Yes | q | EY15 | NONE | Accepted | 04/30/2014
SRP25271 | SREC Solar | CONG | NORTH AMERICA SOLAR CORP | 8500 | Commercial |  | SPRINGFIELD | 08505 | 13 | BLUE SKY TECHNOLOGIES USA | PSE&G | Yes | q | EY16 | NONE | Accepted | 04/30/2014
SRP25272 | SREC Solar | CLANTON | ISE FARMS, INC. | 8157 | Commercial |  | BROADWAY | 08808 | 2 | PVONE, LLC | JCP&L | Yes | q | EY16 | NONE | Accepted | 04/30/2014
SRP25838 | SREC Solar | FAVIUS | BRICK STANDARD, LLC | 6103 | Commercial |  | BRICK | 08723 | 18 | UNITY ELECTRIC LLC | JCP&L | Yes | t |  | NONE | Accepted | 04/30/2014
SRP25898 | SREC Solar | WIEGAND | NORTHPARK SOLAR LLC | 6500 | Commercial |  | MILLSTONE TWP | 08535 | 17 | BAM CONSTRUCTION GROUP, LLC | JCP&L | Yes | q | EY14 | NONE | Accepted | 05/02/2014
SRP26651 | SREC Solar | NIMPHIUS | KDC SOLAR RTC, LLC | 11480 | Commercial |  | EGG HARBOR | 08234 | 19 | THE WHITING-TURNER CONTRACTING COMPANY | AC Electric | Yes | t |  | NONE | Accepted | 06/03/2014
SRP28394 | SREC Solar | RANDALL | MIDFLARE CORP | 2000 | Commercial |  | QUINTON TWP | 08072 | 16 | SELF INSTALL | AC Electric | Yes | q | EY16 | NONE | Accepted | 08/12/2014
SRP28630 | SREC Solar | POTTER | PV NAVIGATOR, LLC | 3897 | Commercial |  | GLOUCESTER | 08083 | 14 | SELF INSTALL | PSE&G | Yes | t |  | NONE | Accepted | 08/20/2014
SRP29548 | SREC Solar | KELLY | KINSLEY LANDFILL | 11180 | Commercial |  | SEWELL | 08080 | 15 | SUNDURANCE ENERGY | PSE&G | Yes | t |  | NONE | Accepted | 09/25/2014
SRP29549 | SREC Solar | JOYCE | PARKLANDS LANDFILL | 10135 | Commercial |  | BORDENTOWN | 08505 | 13 | SUNDURANCE ENERGY | PSE&G | Yes | t |  | NONE | Accepted | 09/25/2014

## Definitions
NJCEP Processing Status Code Definitions
The status codes provided in the project list tab are defined below:
Pipeline Project Status
New (Registration has been received but not reviewed yet.)
Data Entry (Registration is in the project review phase.)
Accepted (SRP Acceptance letter was issued)
Final Data Entry (As built paperwork was received but is incomplete)
Note: Projects that are at the "New" or "Data Entry" status are under review and have not been issued a project acceptance letter from the NJCEP, they are included in the pipeline report but may be subject to change.
Installed Project Status
QC Selected/ QA SELECTED (Final as built documents were received and accepted, project is in QC/QA Inspection phase)
- For program reporting purposes, projects are considered as "Installed" when they reach the QC/QA Selected status.
- Projects that have passed inspection but are missing paper work will remain at QC/QA Selected until the missing items are provided by the applicant.
- Please check for an email communication from the Market Manager processing team after the inspector has notified you that your project passed inspection. If any items are missing please supply them as soon as possible.
Install Complete (All NJCEP requirements have been met, the NJ certification number is in the process of being issued. )
Complete (All NJCEP requirements have been met, the NJ certification number was issued and sent to the registrant and to GATS for verification (see “Sent to GATS Date” column). For rebate program projects, the complete date is the date that the rebate payment check was issued. )

## List Codes
Description of Codes Used In Project List
County Code | County | Subsection Code | Description | EDC Pgm Code | EDC Program Description
1 | Sussex | EDC | EDC Projects | ACE | EDC SREC Financing Program
2 | Warren | q | Subsection q | ACE2 | EDC SREC Financing Program-2
3 | Morris | r | Subsection r | JCPL | EDC SREC Financing Program
4 | Hunterdon | s | Subsection s | JCPL2 | EDC SREC Financing Program-2
5 | Somerset | t | Subsection t | NONE | No Program
6 | Passaic | Blank | Other | PAS | PSEG Pole Attached Solar
7 | Bergen |  |  | PSEG | PSEG Solar Loan 1 and 2
8 | Hudson |  |  | PSEGSL3 | PSEG Solar Loan 3
9 | Essex |  |  | RECO | EDC SREC Financing Program
10 | Union |  |  | RECO2 | EDC SREC Financing Program-2
11 | Middlesex |  |  | S4A1 | PSEG Solar For All 1
12 | Mercer |  |  | S4A2 | PSEG Solar For All 2
13 | Burlington
14 | Camden
15 | Gloucester |  |  | TPO Code | Description
16 | Salem |  |  | 0 | Did Not use TPO
17 | Monmouth |  |  | 1 | Used TPO
18 | Ocean |  |  | Blank | Unknown
19 | Atlantic
20 | Cumberland |  |  | TPO = Third Party Ownership
21 | Cape May
Note: Subsection t projects participating in one of the EDC Finance programs are identified as follows; Subsection t will be selected and the EDC program column will identify the EDC program. The project and its capacity will appear only in the summary table under the subsection t line item to avoid double counting.